## Risk Register
Risk ID | Risk Description | Asset | Threat | Vulnerability / Weakness | Existing Controls | Likelihood | Impact | Inherent Risk | Risk Owner | Treatment | Residual Risk | Status
NCS-R-001 | Unauthorized access to customer and personal data through compromised user credentials. | NCS-A-001 / NCS-A-002 | Credential compromise or account takeover | Incomplete or inconsistent access review and privileged access documentation | MFA; RBAC; Conditional Access; periodic access reviews | 3 | 5 | 15 | Security & Compliance Manager | Mitigate | 10 | Open
NCS-R-002 | Excessive privileges may allow unauthorized access to sensitive systems or information. | NCS-A-004 | Privilege misuse or compromised privileged account | Privileged role assignments are not consistently documented and reviewed | RBAC; MFA; privileged access restrictions; PIM where appropriate | 3 | 5 | 15 | Security & Compliance Manager | Mitigate | 10 | Open
NCS-R-003 | Loss or corruption of customer documents could affect service availability and data integrity. | NCS-A-006 | Data deletion, corruption or storage failure | Backup and recovery procedures are not fully standardized or evidenced | Azure Backup; storage controls; monitoring | 2 | 5 | 10 | IT Operations Manager | Mitigate | 8 | Open
NCS-R-004 | Insufficient monitoring or alerting may delay detection of security incidents. | NCS-A-008 | Security incident or malicious activity | Monitoring coverage and alert review procedures are not consistently documented | Microsoft Sentinel; Azure Monitor; centralized logging | 3 | 4 | 12 | Security Operations Manager | Mitigate | 6 | Open
NCS-R-005 | Unauthorized disclosure of confidential information may occur through inappropriate handling or sharing. | NCS-A-001 | Information disclosure | Information handling practices are not consistently documented across business processes | Information classification scheme; access controls; RBAC | 3 | 4 | 12 | Security & Compliance Manager | Mitigate | 6 | Open
NCS-R-006 | Security weaknesses in application source code could be introduced into production. | NCS-A-002 / NCS-A-009 | Malicious or vulnerable code change | Secure development and code review requirements are not fully documented | GitHub Enterprise; separate environments; access restrictions | 3 | 4 | 12 | Head of Engineering | Mitigate | 8 | Open
NCS-R-007 | A prolonged Azure service disruption could affect the availability of the SaaS platform. | NCS-A-003 / NCS-A-002 | Cloud service outage | Business continuity and recovery requirements are not fully documented for all critical services | Azure availability features; backup; separate environments | 2 | 5 | 10 | Cloud Operations Manager | Mitigate | 6 | Open
NCS-R-008 | Incomplete audit evidence could prevent timely demonstration of control operation. | NCS-A-004 / NCS-A-008 | Audit or certification review | Evidence ownership, storage and retention are not standardized | Microsoft Sentinel; Microsoft 365; internal documentation | 4 | 3 | 12 | Security & Compliance Manager | Mitigate | 6 | Open
NCS-R-009 | Inactive or outdated user accounts may remain enabled longer than required. | NCS-A-004 | Unauthorized use of dormant account | Account lifecycle and periodic review evidence is inconsistent | Entra ID; MFA; account reviews | 3 | 4 | 12 | IT Operations Manager | Mitigate | 6 | Open
NCS-R-010 | Failure to maintain current security and compliance documentation could lead to control gaps. | NCS-A-004 / NCS-A-008 | Governance or compliance failure | Policies, procedures and control documentation are not consistently maintained | Security & Compliance function; internal policies; periodic reviews | 4 | 3 | 12 | Security & Compliance Manager | Mitigate | 6 | Open
NCS-R-011 | Loss of access to critical encryption keys could affect protected data and service operation. | NCS-A-007 | Key deletion, compromise or unavailability | Key management procedures and recovery arrangements are not fully evidenced | Azure Key Vault; access controls; monitoring | 2 | 5 | 10 | Security & Compliance Manager | Mitigate | 5 | Open
NCS-R-012 | External or customer-facing integrations may introduce uncontrolled security dependencies. | NCS-A-002 | Third-party compromise or integration failure | Third-party security requirements and dependency reviews are not consistently documented | Network controls; RBAC; monitoring; contractual requirements | 3 | 4 | 12 | Security & Compliance Manager | Mitigate | 8 | Open

## Lists
Status | Treatment | Risk Owner
Open | Mitigate | Security & Compliance Manager
In Progress | Accept | IT Operations Manager
Accepted | Transfer | Cloud Operations Manager
Closed | Avoid | Security Operations Manager
Requires Review |  | Head of Engineering